## Slide 1
OSIP — ONE-STOP INVESTMENT PLATFORM
Feedback Review — Changes Made & Incorporated
Changes have been made on the basis of the feedback received, and the requested revisions have been incorporated into the platform.
This deck summarises what has been completed, what remains, and the inputs we need from your side to move into the development phase.
Source: OSIP Feedback Changes v0.1 (4 Sep 2026), 109-item log · Status as of 21 Sep 2026

## Slide 2
OVERALL PROGRESS
Total Changes — Done vs. Pending
Of the 109 feedback items logged, the large majority are already implemented in the code.
Status | Meaning | Count
Done | Implemented in code as requested | 94
Partial | Partly done — a specific gap remains | 5
Dev phase | Deferred to the development / build phase | 6
Not done | Open prototype item | 1
Total | All logged feedback items | 109
94 / 109
changes completed
Remaining 15 items are either small gaps, deferred to the development phase, or awaiting a client decision.
Still open: 5 partial (items 27, 56, 58, 66, 104) · 6 deferred to dev phase (16, 53, 94, 95, 96, 102) · 1 not done (74 — dated 'coming soon' placeholders).

## Slide 3
BY AREA
What Was Addressed — Across the Platform
Area | Items | Done | Note on remaining
Homepage & Hero | 11 | 11 | 
Navigation, Menu & Search | 6 | 5 | 16 breadcrumbs → dev phase
Sector Pages | 6 | 6 | copy shortening: Solar first
Regulations | 7 | 6 | 27 tag chips partial
Opportunities & Investment | 15 | 14 | 36 server-lock at deploy
Data & Insights | 5 | 5 | 
Login & Investor Dashboard | 9 | 6 | 53 captcha → dev; 56/58 partial
Forms & Contact | 7 | 6 | 66 states partial
Trust, Accuracy & Naming | 15 | 14 | 74 placeholders open
Accessibility | 8 | 8 | 
Mobile | 3 | 3 | 
Technical, Perf. & Privacy | 5 | 2 | 94/95/96 → dev phase
Support, News & Events | 7 | 6 | 102 alerts → dev phase
Climate Finance & Partnerships | 5 | 5 | 109 domain decision pending

## Slide 4
SECTOR PAGES
Sectors — Solar Done as the Template
For the sector pages, we have currently edited only “Solar”.
Solar (DetailedSector.html) has been reworked as the approved template — shortened, investor-facing copy, standardised section order, and the new supporting components.
If this direction is acceptable to you, we will implement the same across all 10 sectors during the development phase.
Applied on the Solar template:
• Standardised section order across the page (Overview → Key Facts → How Investors Can Participate → Regulations → Technical & Safety → Finance → Opportunities → Resources).
• Shortened, investor-facing copy (item 23) — the same reduction to be rolled out to the other 9 sectors.
• Named MDAs with a one-line role note, glossary term definitions, and linked financial-institution summaries.
• Lazy-loaded video facade and contextual “incentives are not automatic” notes.

## Slide 5
ACTION NEEDED FROM YOUR SIDE
Major Blockers / Inputs Required
To move into the development phase without delay, we need the following from your side:
1
Domain name & ownership details
We need the confirmed domain name and its ownership / governance details (the portal-ownership model, D1 / D29).
Required by 5 October 2026
2
Content to be uploaded
The real content that needs to be uploaded to the platform — copy, documents, figures, contacts and imagery — to replace the current placeholders.
Required by 5 October 2026
Why it matters: these two inputs are the primary blockers. Development can proceed on schedule only once the domain/ownership is confirmed and the content package is received.

## Slide 6
NEXT STEPS
What We Need Next — Timeline
Within the next 3 days
Please share your feedback on the design changes
We would like your review of the design changes (and any other revisions) within the next three days, so we can finalise and incorporate them.
By 1 October 2026
We will be ready with the agreed changes
We will have the requested design and review changes ready and incorporated by 1 October.
By 5 October 2026
Domain name & ownership + content to upload
We need the confirmed domain name / ownership details and the content package to be uploaded, so development can proceed.